## Protokoll
Meetingprotokoll: | [5 empty] | Projektstatus - Meeting Releasewechsel T&I-Portal | [5 empty] | Elbert
Kohlsdorf
M-Nr. | Meetingtitel |  |  | Datum |  | Teilnehmer |  | abwesend |  |  |  | Lang
1 | Kick-Off | [10 empty] | Mielke
2 | Entwicklung SocialNetworkConnector |  |  | 2014-11-03 |  | Christian Günther / Maic Rittmeier / Magnus Leinemann / Thomas Nowak | [5 empty] | Osterkamp
3 | [11 empty] | Schmitz
4 | [11 empty] | Schmitz
5 | [11 empty] | Schmitz
6 | [11 empty] | Schmitz
7 | [11 empty] | Schmitz
8 | [11 empty] | Winter
9 | [11 empty] | Winter
10 | [11 empty] | Winter
11 | [11 empty] | Winter
12 | [11 empty] | Winter
13 | [11 empty] | Winter
14 | [11 empty] | Winter
15 | [11 empty] | Winter
16 | [11 empty] | Winter
17 | [11 empty] | Winter
18
19
20
21
22
23
24
25
Nr. | M- Nr. | Datum | Art | Teilprojekt | Version | Inhalt | Bereich / Komponente | Verantwortlich | zu erledigen bis | Erledigt am | Werte für Projektgruppe | Pavlic
1 | 2 | 2014-11-03 | B | SNC | 0,9 | TODO fix error while inserting/updating dataset with SQL | HANAPersistence.java |  |  |  | Projektleitung
2 | 2 | 2014-11-03 | B | SNC | 0,9 | TODO make parser work when using threads instead of messages | LithiumCrawler.java |  |  |  | Entwickler
3 | 2 | 2014-11-03 | B | SNC | 0,9 | TODO change this to string does not need to be long and creates only issues with the web parser | PostData.java |  |  |  | Tester intern
4 | 2 | 2014-11-03 | B | SNC | 0,9 | TODO implement possibility have black-list of combinations not to track: e.g. Depot YES / Home Depot NO | TwitterCrawler.java |  |  |  | Tester Kunde
5 | 2 | 2014-11-03 | B | SNC | 0,9 | TODO implement SimpleWebCrawler to retrieve a web-page referenced in a tweet by a hyperlink | TwitterCrawler.java |  |  |  | Sonstige 2
6 | 2 | 2014-11-03 | B | SNC | 0,9 | TODO check if this class is usable for other social networks | LocationData.java |  |  |  | Sonstige 3
7 | 2 | 2014-11-03 | B | SNC | 0,9 | TODO implement proper data handling for site and user | WOPageWebParser.java
8 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement code to retrieve geo location elements from json file | FsCrawler.java
9 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO check why the crawler does not work correctly in case the dataCryptoProvider is activated | FsCrawler.java
10 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO make savePost generic to deal with different persistence managers at runtime | FsCrawler.java
11 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO check if we need a generic input type for anything and if not delete this class | GenericInputType.java
12 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO enable geoLocation support for users | HANAPersistence.java
13 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO check if we need to safe the thread from which the posting originated | LithiumPostingData.java
14 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO check if we can make use of threads and if threads may be the proper field instead of board | LithiumPostingData.java
15 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO Add support for labels | LithiumPostingData.java
16 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO check if we need to support for the anonymous and deleted flag | LithiumUserData.java
17 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement geo geoLocation support for users | LithiumUserData.java
18 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO check if we shall make use of geotools (http://docs.geotools.org/latest/userguide/faq.html) | LocationData.java
19 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO get rid of this. it is only needed for the HttpErrorMessages and HttpStatusCode Implementation | pom.xml
20 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO move GeneralDataDefinitions to RuntimeConfiguration and source it in from XML | PostData.java
21 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO find out how to use executor Service for multi threaded persistence call | SimpleWebCrawler.java
22 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement execute method in SompleWebParser to make it thread save | SimpleWebParser.java
23 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement language detection (possibly with jroller http://www.jroller.com/melix/entry/jlangdetect_0_3_released_with) | SimpleWebParser.java
24 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement language recognition | SimpleWebParser.java
25 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement language recognition | SimpleWebParser.java
26 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement correct threaded parser to aid in multithreading | SimpleWebParser.java
27 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO Implement proper algorithm to deal with hashtags | TwitterPostingData.java
28 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO Implement proper algorithm to deal with user mentions | TwitterPostingData.java
29 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO Implement proper algorithm to deal with symbols | TwitterPostingData.java
30 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement proper language detection | WONewsWebParser.java
31 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement language detection (possibly with jroller http://www.jroller.com/melix/entry/jlangdetect_0_3_released_with) | WONewsWebParser.java
32 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement language detection (possibly with jroller http://www.jroller.com/melix/entry/jlangdetect_0_3_released_with) | WOPageWebParser.java
33 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement proper language detection | WOPageWebParser.java
34 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement execute-method to make parser thread save | WONewsWebParser.java
35 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement run method for multi threaded parsing | WONewsWebParser.java
36 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement proper language detection | WOPostingWebParser.java
37 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement language detection (possibly with jroller http://www.jroller.com/melix/entry/jlangdetect_0_3_released_with) | WOPostingWebParser.java
38 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement run method for multi threaded parsing | WOPageWebParser.java
39 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement execute-method to make parser thread save | WOPageWebParser.java
40 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO extract user information from the website | WONewsWebParser.java
41 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement correct threaded parser to aid in multithreading | WOPageWebParser.java
42 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO extract user information from the website | WOPostingWebParser.java
43 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement run method for multi threaded parsing | WOPostingWebParser.java
44 | 2 | 2014-11-03 | B | SNC | 1,0 | TODO implement execute-method to make parser thread save | WOPostingWebParser.java
45 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO check implementation to provide for arbitrary data types while preserving type safety | CrawlerConfiguration.java
46 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO implement facebook data parser | FacebookParser.java
47 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO implement real code | FacebookPosting.java
48 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO create implementation for facebook posting data | FacebookPostingData.java
49 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO Implement algorithm to deal with user mentions | FacebookPostingData.java
50 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO Implement algorithm to deal with symbols | FacebookPostingData.java
51 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO Implement algorithm to deal with hashtags | FacebookPostingData.java
52 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO implement code for facebook user handling | FacebookUser.java
53 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO establish proper error handling to get the HTTP error code from OData calls | HANAPersistence.java
54 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO change data retrieval to use getResponseBodyAsStream - fixes warning: Going to buffer response body of large or unknown size. Using getResponseBodyAsStream instead is recommended. | LithiumCrawler.java
55 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO implement jericho to truncate html | LithiumPostingData.java
56 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO add support for average_rating_value, average_posting_rating_value and average_posting_ratio | LithiumUserData.java
57 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO check if user profile can and shall be used | LithiumUserData.java
58 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO use nodelist instead of single expressions for each node | RuntimeConfiguration.java
59 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO check if we can use getResponseBodyAsStrema to fix the following warning: Going to buffer response body of large or unknown size. Using getResponseBodyAsStream instead is recommended. | TwitterCrawler.java
60 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO move this in RuntimeConfiguration and source it in from XML | TwitterPostingData.java
61 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO move this in RuntimeConfiguration and source it in from XML | TwitterPostingData.java
62 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO move this in RuntimeConfiguration and source it in from XML | TwitterPostingData.java
63 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO move this in the crypto package, as really MD5 is a crypto provider of sorts | UniqueIdServices.java
64 | 2 | 2014-11-03 | B | SNC | 1,5 | TODO implement proper handling of hashtags, symbols and mentions - this currently kills the parser | TwitterPostingData.java
65 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO implement encryption method | Base64CryptoProvider.java
66 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO implement method to create new configuration-file | ComplexXmlConfigurationPersistence.java
67 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO implement code to retrieve one single configuration element | ComplexXmlConfigurationPersistence.java
68 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO implement code to update a single configuration element | ComplexXmlConfigurationPersistence.java
69 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO implement encryption method | DesCryptoProvider.java
70 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO implement code to retrieve a single element from the configuration file | IniFileConfigurationPersistence.java
71 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO implement code to insert/update a value in the configuration file | IniFileConfigurationPersistence.java
72 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO implement code to write the configuration file back to disk | IniFileConfigurationPersistence.java
73 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO implement code to retrieve one single configuration element | SimpleXmlConfigurationPersistence.java
74 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO implement code to update a configuration element | SimpleXmlConfigurationPersistence.java
75 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO implement writeNewConfiguration | SimpleXmlConfigurationPersistence.java
76 | 2 | 2014-11-03 | B | SNC | 2,0 | TODO add field db_entry with timestamp on creation time | TwitterUserNeo4JNode.java
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## Change Request Liste
Change Requests |  |  | Releasewechsel T&I Portal
Nr. | Datum | Teilprojekt | Inhalt | Aufwand in Tagen | Status | Bemerkung | eingereicht |  | genehmigt am | geplant für | umgesetzt |  | abgerechnet auf
[7 empty] | von | am |  |  | von | am | Kontrakt | Pos. | Werte für Projektgruppe | Werte für Status | Werte für "geplant für"
1 | 2014-11-03 | SNC 0.9 | Bereitstellung des Beta-Releases (Version 0.9) des SocialNetworkConnector (SNC) für den Pilotbetrieb bei der Cortal Consors | 100 | genehmigt | [9 empty] | SNC | neu | 2014-11-01
[15 empty] | HANA | beantragt | 2014-12-01
[15 empty] | iPad App | genehmigt | 2015-04-01
umgesetzt
abgelehnt
zurückgestellt
nicht relevant
ersetzt durch anderen CR
ausgerollt
abgeschlossen