## ToDos SNC
Nr | Beschreibung | Area | Prio | Fixed | Fix in Release | Owner | Due-Date | Datei | Pfad im Projekt | Codezeile | Typ
2 | TODO fix error while inserting/updating dataset with SQL | Persistence | Prio 1 |  | 0.9 |  |  | HANAPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 65 | Java Task
43 | TODO make parser work when using threads instead of messages | Crawler | Prio 1 |  | 0.9 |  |  | LithiumCrawler.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crawler | line 79 | Java Task
11 | TODO change this to string does not need to be long and creates only issues with the web parser | Data | Prio 1 | YES | 0.9 |  |  | PostData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 53 | Java Task
16 | TODO implement possibility have black-list of combinations not to track: e.g. Depot YES / Home Depot NO | Crawler | Prio 1 |  | 0.9 |  |  | TwitterCrawler.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crawler | line 73 | Java Task
17 | TODO implement SimpleWebCrawler to retrieve a web-page referenced in a tweet by a hyperlink | Crawler | Prio 1 |  | 0.9 |  |  | TwitterCrawler.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crawler | line 241 | Java Task
83 | TODO check if this class is usable for other social networks | Data | Prio 1 |  | 0.9 |  |  | LocationData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 38 | Java Task
21 | TODO implement proper data handling for site and user | Parser | Prio 1 |  | 0.9 |  |  | WOPageWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 51 | Java Task
54 | TODO implement code to retrieve geo location elements from json file | Data | Prio 2 |  | 1.0 |  |  | FsCrawler.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crawler | line 430 | Java Task
55 | TODO check why the crawler does not work correctly in case the dataCryptoProvider is activated | Data | Prio 2 |  | 1.0 |  |  | FsCrawler.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crawler | line 118 | Java Task
57 | TODO make savePost generic to deal with different persistence managers at runtime | Data | Prio 3 |  | 1.0 |  |  | FsCrawler.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crawler | line 140 | Java Task
49 | TODO check if we need our own executor service and if not delete this class | Thread | Prio 3 |  | 1.0 |  |  | GenericExecutorService.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/handler | line 25 | Java Task
51 | TODO check if we need a generic input type for anything and if not delete this class | Data | Prio 3 |  | 1.0 |  |  | GenericInputType.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 14 | Java Task
6 | TODO enable geoLocation support for users | Data | Prio 2 |  | 1.0 |  |  | HANAPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 67 | Java Task
37 | TODO check if we need to safe the thread from which the posting originated | Data | Prio 3 |  | 1.0 |  |  | LithiumPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 74 | Java Task
38 | TODO check if we can make use of threads and if threads may be the proper field instead of board | Data | Prio 2 |  | 1.0 |  |  | LithiumPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 349 | Java Task
40 | TODO Add support for labels | Data | Prio 2 |  | 1.0 |  |  | LithiumPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 72 | Java Task
76 | TODO check if we need to support for the anonymous and deleted flag | Data | Prio 2 |  | 1.0 |  |  | LithiumUserData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 45 | Java Task
78 | TODO implement geo geoLocation support for users | Data | Prio 3 |  | 1.0 |  |  | LithiumUserData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 43 | Java Task
85 | TODO check if we shall make use of geotools (http://docs.geotools.org/latest/userguide/faq.html) | Data | Prio 2 |  | 1.0 |  |  | LocationData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 37 | Java Task
52 | TODO get rid of this. it is only needed for the HttpErrorMessages and HttpStatusCode Implementation | Config | Prio 3 |  | 1.0 |  |  | pom.xml | /socialnetworkconnector | line 231 | XML Task
13 | TODO move GeneralDataDefinitions to RuntimeConfiguration and source it in from XML | Config | Prio 2 |  | 1.0 |  |  | PostData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 28 | Java Task
44 | TODO find out how to use executor Service for multi threaded persistence call | Thread | Prio 2 |  | 1.0 |  |  | SimpleWebCrawler.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crawler | line 465 | Java Task
31 | TODO implement execute method in SompleWebParser to make it thread save | Thread | Prio 2 |  | 1.0 |  |  | SimpleWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 250 | Java Task
32 | TODO implement language detection (possibly with jroller http://www.jroller.com/melix/entry/jlangdetect_0_3_released_with) | Lang | Prio 1 |  | 1.0 |  |  | SimpleWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 58 | Java Task
33 | TODO implement language recognition | Lang | Prio 1 |  | 1.0 |  |  | SimpleWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 302 | Java Task
34 | TODO implement language recognition | Lang | Prio 1 |  | 1.0 |  |  | SimpleWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 291 | Java Task
41 | TODO implement correct threaded parser to aid in multithreading | Thread | Prio 2 |  | 1.0 |  |  | SimpleWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 57 | Java Task
5 | TODO Implement proper algorithm to deal with hashtags | Data | Prio 1 |  | 1.0 |  |  | TwitterPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 267 | Java Task
7 | TODO Implement proper algorithm to deal with user mentions | Data | Prio 1 |  | 1.0 |  |  | TwitterPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 249 | Java Task
8 | TODO Implement proper algorithm to deal with symbols | Data | Prio 1 |  | 1.0 |  |  | TwitterPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 258 | Java Task
26 | TODO implement proper language detection | Lang | Prio 1 |  | 1.0 |  |  | WONewsWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 94 | Java Task
30 | TODO implement language detection (possibly with jroller http://www.jroller.com/melix/entry/jlangdetect_0_3_released_with) | Lang | Prio 1 |  | 1.0 |  |  | WONewsWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 44 | Java Task
22 | TODO implement language detection (possibly with jroller http://www.jroller.com/melix/entry/jlangdetect_0_3_released_with) | Lang | Prio 1 |  | 1.0 |  |  | WOPageWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 52 | Java Task
23 | TODO implement proper language detection | Lang | Prio 1 |  | 1.0 |  |  | WOPageWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 104 | Java Task
27 | TODO implement execute-method to make parser thread save | Thread | Prio 2 |  | 1.0 |  |  | WONewsWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 72 | Java Task
28 | TODO implement run method for multi threaded parsing | Thread | Prio 2 |  | 1.0 |  |  | WONewsWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 66 | Java Task
70 | TODO implement proper language detection | Lang | Prio 1 |  | 1.0 |  |  | WOPostingWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 94 | Java Task
71 | TODO implement language detection (possibly with jroller http://www.jroller.com/melix/entry/jlangdetect_0_3_released_with) | Lang | Prio 1 |  | 1.0 |  |  | WOPostingWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 45 | Java Task
19 | TODO implement run method for multi threaded parsing | Thread | Prio 2 |  | 1.0 |  |  | WOPageWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 73 | Java Task
20 | TODO implement execute-method to make parser thread save | Thread | Prio 2 |  | 1.0 |  |  | WOPageWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 77 | Java Task
29 | TODO extract user information from the website | Parser | Prio 1 |  | 1.0 |  |  | WONewsWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 45 | Java Task
24 | TODO implement correct threaded parser to aid in multithreading | Thread | Prio 2 |  | 1.0 |  |  | WOPageWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 50 | Java Task
73 | TODO extract user information from the website | Parser | Prio 1 |  | 1.0 |  |  | WOPostingWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 46 | Java Task
74 | TODO implement run method for multi threaded parsing | Thread | Prio 2 |  | 1.0 |  |  | WOPostingWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 66 | Java Task
75 | TODO implement execute-method to make parser thread save | Thread | Prio 2 |  | 1.0 |  |  | WOPostingWebParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 72 | Java Task
62 | TODO check implementation to provide for arbitrary data types while preserving type safety | Config | Prio 2 |  | 1.5 |  |  | CrawlerConfiguration.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/appstate | line 35 | Java Task
1 | TODO implement facebook data parser | Data | Prio 3 |  | 1.5 |  |  | FacebookParser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/parser | line 34 | Java Task
39 | TODO implement real code | Data | Prio 3 |  | 1.5 |  |  | FacebookPosting.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/handler | line 41 | Java Task
58 | TODO create implementation for facebook posting data | Data | Prio 3 |  | 1.5 |  |  | FacebookPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 50 | Java Task
59 | TODO Implement algorithm to deal with user mentions | Data | Prio 3 |  | 1.5 |  |  | FacebookPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 231 | Java Task
60 | TODO Implement algorithm to deal with symbols | Data | Prio 3 |  | 1.5 |  |  | FacebookPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 240 | Java Task
61 | TODO Implement algorithm to deal with hashtags | Data | Prio 3 |  | 1.5 |  |  | FacebookPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 249 | Java Task
50 | TODO implement code for facebook user handling | Data | Prio 3 |  | 1.5 |  |  | FacebookUser.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/handler | line 36 | Java Task
4 | TODO establish proper error handling to get the HTTP error code from OData calls | Persistence | Prio 2 |  | 1.5 |  |  | HANAPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 66 | Java Task
45 | TODO change data retrieval to use getResponseBodyAsStream - fixes warning: Going to buffer response body of large or unknown size. Using getResponseBodyAsStream instead is recommended. | Crawler | Prio 3 |  | 1.5 |  |  | LithiumCrawler.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crawler | line 78 | Java Task
42 | TODO implement jericho to truncate html | Parser | Prio 3 |  | 1.5 |  |  | LithiumPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 73 | Java Task
77 | TODO add support for average_rating_value, average_posting_rating_value and average_posting_ratio | Data | Prio 2 |  | 1.5 |  |  | LithiumUserData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 46 | Java Task
79 | TODO check if user profile can and shall be used | Crawler | Prio 2 |  | 1.5 |  |  | LithiumUserData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 44 | Java Task
3 | TODO instantiate the Web-Parser via parserControl | Parser | Prio 3 |  | 1.5 |  |  | MultiWebCrawler.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crawler | line 79 | Java Task
18 | TODO use nodelist instead of single expressions for each node | Config | Prio 3 |  | 1.5 |  |  | RuntimeConfiguration.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/appstate | line 64 | Java Task
15 | TODO check if we can use getResponseBodyAsStrema to fix the following warning: Going to buffer response body of large or unknown size. Using getResponseBodyAsStream instead is recommended. | Crawler | Prio 3 |  | 1.5 |  |  | TwitterCrawler.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crawler | line 72 | Java Task
9 | TODO move this in RuntimeConfiguration and source it in from XML | Config | Prio 2 |  | 1.5 |  |  | TwitterPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 143 | Java Task
12 | TODO move this in RuntimeConfiguration and source it in from XML | Config | Prio 3 |  | 1.5 |  |  | TwitterPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 115 | Java Task
14 | TODO move this in RuntimeConfiguration and source it in from XML | Config | Prio 2 |  | 1.5 |  |  | TwitterPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 131 | Java Task
72 | TODO move this in the crypto package, as really MD5 is a crypto provider of sorts | Config | Prio 3 |  | 1.5 |  |  | UniqueIdServices.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/helper | line 20 | Java Task
10 | TODO implement proper handling of hashtags, symbols and mentions - this currently kills the parser | Data | Prio 2 |  | 1.5 |  |  | TwitterPostingData.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/data | line 237 | Java Task
53 | TODO implement encryption method | Data | Prio 3 |  | 2.0 |  |  | Base64CryptoProvider.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crypto | line 55 | Java Task
63 | TODO implement method to create new configuration-file | Config | Prio 2 |  | 2.0 |  |  | ComplexXmlConfigurationPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 429 | Java Task
64 | TODO implement code to retrieve one single configuration element | Config | Prio 3 |  | 2.0 |  |  | ComplexXmlConfigurationPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 418 | Java Task
65 | TODO implement code to update a single configuration element | Config | Prio 2 |  | 2.0 |  |  | ComplexXmlConfigurationPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 424 | Java Task
84 | TODO implement encryption method | Data | Prio 3 |  | 2.0 |  |  | DesCryptoProvider.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/crypto | line 95 | Java Task
66 | TODO implement code to retrieve a single element from the configuration file | Config | Prio 3 |  | 2.0 |  |  | IniFileConfigurationPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 114 | Java Task
67 | TODO implement code to insert/update a value in the configuration file | Config | Prio 3 |  | 2.0 |  |  | IniFileConfigurationPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 121 | Java Task
68 | TODO implement code to write the configuration file back to disk | Config | Prio 3 |  | 2.0 |  |  | IniFileConfigurationPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 127 | Java Task
56 | TODO make registering a relationship work | Persistence | Prio 3 |  | 2.0 |  |  | Neo4JEmbeddedDB.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/neo4j | line 108 | Java Task
47 | TODO implement code to check if a node already exists prior inserting one | Persistence | Prio 3 |  | 2.0 |  |  | Neo4JPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 53 | Java Task
48 | TODO implement code for graph traversal | Persistence | Prio 3 |  | 2.0 |  |  | Neo4JPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 54 | Java Task
80 | TODO implement code to retrieve one single configuration element | Config | Prio 3 |  | 2.0 |  |  | SimpleXmlConfigurationPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 194 | Java Task
81 | TODO implement code to update a configuration element | Config | Prio 3 |  | 2.0 |  |  | SimpleXmlConfigurationPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 201 | Java Task
82 | TODO implement writeNewConfiguration | Config | Prio 3 |  | 2.0 |  |  | SimpleXmlConfigurationPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 207 | Java Task
25 | TODO add field db_entry with timestamp on creation time | Data | Prio 3 |  | 2.0 |  |  | TwitterUserNeo4JNode.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/neo4j | line 49 | Java Task
35 | TODO check implementation of geo geoLocation | Persistence | Prio 3 |  | 2.0 |  |  | Neo4JPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 138 | Java Task
36 | TODO check implementation of geo geoLocation | Persistence | Prio 3 |  | 2.0 |  |  | Neo4JPersistence.java | /socialnetworkconnector/src/main/java/de/comlineag/snc/persistence | line 55 | Java Task
69 | TODO get rid of this. it is only needed for the HttpErrorMessages and HttpStatusCode Implementation |  | Prio 3 | OBSOLETE |  |  |  | pom_VERSION_0_3_4.xml | /socialnetworkconnector/Documentation | line 183 | XML Task
46 | TODO get rid of this. it is only needed for the HttpErrorMessages and HttpStatusCode Implementation |  | Prio 3 | OBSOLETE |  |  |  | pom_VERSION_0_5_0.xml | /socialnetworkconnector/Documentation | line 107 | XML Task